## Sheet1
Home Build Schedule |  |  | Day 1 Build Date
Address: 207 W North St - Elida |  |  | 2019-07-27
Schedule | Date Need by | Description of Jobs | Who | # Vol
Day 1 Build: 8AM-Noon | 2019-07-27 | Erect outside walls, Plumb & Brace walls, install inside walls and top plates, scaffolding low | Volunteer | 8-12
Day 1 Build: 10AM-2PM | 2019-07-27 | Set scaffolds for truss install | V | 6-8
Day 1 Build: Noon-5PM | 2019-07-27 | Install trusses, lateral bracing, 2x6 facia, 1st row sheeting, raise trusses, finish sheeting, felt, drip edge. | V | 8-12
Week2 | 2019-07-29 | sidewalks & porch poured, Insulate tub wall. Install drywall vent box and vent to outside. | Subcontractor, v | 12
Build Day 2: 8AM-3PM | 2019-08-03 | Install truss bracing, hurricane clips, lateral supports, install styro & tape, caulk exterior walls to floor and OSB, caulk top plates and double studs, install door frames and temp doors | V | 12-15
Week 3 | 2019-08-05 | Shingles to roof, Build Front porch roof | V, Sub | 6
Day 3 Build: 8AM-3PM | 2019-08-10 | Build shed, box corners on roof, Build porch roof. | V | 12-15
Week 4 | 2019-08-12 | Begin electric & plumbing rough-in, Pour front porch and sidewalks, shingle roof and shed | Subs
Day 4 Build: 8AM-3PM | 2019-08-17 | Cut windows, install and tape styro, Install doors., scaffolds & guradrails down and return to shop, f channel, soffit, facia metal, Porch ceiling complete, Windows installed | V | 12-15
Week 5 | 2019-08-19 | Siding starter and corners, Rough-in electric, rough-in plumbing complete, CAT 5 runs, bath vent, call for electric, remove pole | V/Sub, PM | 2-4
Day 5 Build: 8AM-3PM | 2019-08-24 | Siding Installed, Prime & Paint shed |  | 10-15
Week 6 | 2019-08-26 | Drywall blocks, rail backers, insul netting installed, |  | 2
Day 6 Build: 8AM-3PM | 2019-08-31 | Wall insulation installed | V | 12
Week 7 | 2019-09-02 | catch up all projects | V | 4-6
Day 7 Build: 8AM-3PM | 2019-09-07 | Finish siding, bath vent, crawl access | V | 43624
Week 8 | 2019-09-09 | catch up all projects | Sub/v | 6
Day 8 Build: 8AM-3PM | 2019-09-14 | Drywall installation | V | 8-12
Week 9 | 2019-09-16 | Drywall Finishing, size cabinets and doors | Sub, Pm | 0
Day 9 Build: 8AM-Noon & Noon-4PM | 2019-09-21 | Catch up on all projects | V | 6-8
Week 10 | 2019-09-23 |  | V | 4
Day 10 Build | 2019-09-28 | Painting Day, Prime AM, Paint PM | V | 8-10, 8-10
Week 11 | 2019-09-30 | Finish electric, vinyl flooring, Finish HVAC | Sub | 0
Day 11 Build | 2019-10-05 | Cabinets installed | Sub | 0
Week 12 | 2019-10-07 | Flooring completed | Sub,V | 3
Day 12 Build Day: 8AM-3PM | 2019-10-12 | Interior doors counter top installed | V | 4
Week 13 | 2019-10-14 | Base Moldlings | V | 3
Day 13 Build: 8AM-3PM | 2019-10-19 | Interior doors, trim, door handles, bath rails, closet shelves, pantry shelves, crawl & attic accesses | Sub, V | 6-8
Week 14 | 2019-10-21 | Range vent, cabinet hardware, shutters, mailbox, blinds, bath mirrors | V | 4
Day 14 Build | 2019-10-26 | Storm Doors, Move tool trailer, clean out shed, Clean windows and house, change door locks. | V | 4
Week 15 | 2019-10-28 | Carpet (if desired), Final inspections, All materials and trailers gone | V | 4
Dedication | 2019-11-03 | DEDICATION SUNDAY | ALL | ALL
|  | Landscape & Seed, | Sub
Formulas:
Date Need by = +[Date Need by, row above]+5

## Sheet2
Home Buiild Schedule |  |  | Day 1 Build Date
Address: 207 W North St. Elida |  |  | 2019-06-01
Schedule | Date Need by | Description of Jobs | Who | # Vol
Decide on Family, purchase lot and House plans completed | 2019-04-02 |  | Board
Plans Finalized | 2019-04-22 | Call about Versa lift, Ask about boom also. | Crouse, Bobcat
Plans Submitted | 2019-04-23 | Permit fee $20 | Me/City
Layout walls in Construction Room | 2019-04-23 |  | PM,V | 2-3
Begin Wall Build | 2019-04-27 | Build door & window openings, build walls | PM, V | 4-6
Continue Wall Build | 2019-04-29 | Build door & window openings, build walls | PM, V | 4-6
Begin Excavation/Concrete | 2019-04-30 | Call for porta pot, driveway & shed stone installed, | Sub
Pre Build Complete | 2019-05-06 | All Walls marked for location, truss locations, cross plate/wall locations | V, PM | 4-6
Finish Concrete/excavation | 2019-05-05 | Level ground around house, Install temp. Electric | Sub
Job Trailer to Site | 2019-05-24 | Material Storage Trailer? | Joe
Build Floor | 2019-05-25 | plate, beam, I joists, Squash, OSB, 2" stryo, caulk plate to foundation, layout walls on floor. | PM | 12-15
Move walls to site | 2019-05-27 | Layout walls on floor | PM | 2-4
Week -1 | 2019-05-27 | Materials to site, Build end trusses and fly rafters, add guard rails | v | 8-12
Truss lifter to Site | 2019-05-31 |  | PM
Formulas:
Date Need by = +[Date Need by, row above]+1
Date Need by = +[Date Need by, row below]-1

## Sheet3
Habitat Construction
Pre-Build Day Schedule of Events
Description | Date | # Vounteers | 8:00 | 8:15-8:30 | 9:00 | 10:00 | 10:30 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00
Pre-Floor Build Projects | 2019-07-19 | Crouse | Floor Materials to job site
|  | 2 |  |  | Layout Sill plate with sill seal, square and secure
|  | 2 |  |  |  | Mark joist locations
|  | 4 to 6 ( two to cut and run) |  |  |  |  | Begin building Main Beam, level to sill plate
|  | 4 to 6 | [6 empty] | Complete Beam assembly
Lunch
|  | 2 | [7 empty] | Secure jacks to beam and pads (relevel)
|  | 1 | [8 empty] | Install 2" x32" Styro to crawl space walls
|  | 3 | [8 empty] | Layout and install Rim Joist
Floor Build Day | 2019-07-20 | All | Welcome, Meet and go over plan, sign in
|  | 4 to 6 (1 cut, 2 run) |  | Begin cutting joist to length, install 16 on center as marked.
|  | 4 to 6 |  |  |  |  | Complete joist install (all full length I joists)
|  | 4 (2 for cut and run) |  |  |  |  | Begin Cut in for crawl access
|  | 2 |  |  |  |  | Straighten I joists and secure with batten
|  | 2 |  |  |  |  | Begin installation of Squash blocks
|  | All | [6 empty] | Lunch
|  | 3 | [7 empty] | Begin gluing and setting floor panels, nail 4 corners
|  | 2 | [7 empty] | Nail the field
Chalk and spray wall locations
|  | 4 | [10 empty] | Tarp the deck and secure
|  | 2 to 6 | [10 empty] | Clean up scrap and tools
Week Prior to Build Day 1 | 2019-07-23 | 4 to 6 | Scaffolding to jobsite
|  | Rindler | Trusses and shed frame to job site
|  | Crouse | Build Day materials to job site (Cover or in material trailer)
|  | 2 to 4 |  |  | Build End-Truss fly rafters. Add Guard Rails
| 2019-07-25 | 8 to 12 | Load Outside walls to take to job site
|  | 8 to 12 |  |  | Stack outside walls on deck in 4 piles (cover)
|  | 8 to 12 |  |  |  |  | Load Inside walls to take to job site
|  | 8 to 12 | [5 empty] | Stack and cover inside walls (cover)
| 2019-07-26 | PM | [7 empty] | Versa lift to job site

## Sheet4
Habitat Contruction: Build Day 1 Tasks
Address: 207 W North st - Elida
Description | # Vounteers | 8:00-8:30 | 8:30 | 9:00 | 10:00 | 10:30 | 11:00 | 12:00 | 13:00 | 14:00 | 14:30 | 15:00 | 16:00 | 17:00
Opening | All | Meet, sign in, Intro of family and Leaders
Begin Morning Build 1st crew | 8-12 |  | Walls moved to floor (stacked by location)
Work from 1st corner in groups | 4 to move, 2 to bolt, 2 to brace and plumb, 2 to cut and carry) |  |  | Outside Wall sections bolted together and to floor wall by wall, plumbed & braced
Break | All |  |  |  | Break
Enter Scaffold Crew | 8-12 |  |  |  | Scaffold Crew meet, sign in
Inside walls | 2 to set, 2 to bolt, 2 to brace and plumb |  |  |  |  | Inside wall sections added in, plumbed and braced
Scaffold Group Begins | 2 to set brackets, 4 to install walking boards (no guard rails yet) |  |  |  |  | Scaffolds installed on outside walls (set low every 8 feet from inside side wall)
Finish walls and true them | 4-6 to | [5 empty] | Double check plumb on all walls and bracing
Break | All | [6 empty] | Lunch
Enter Roof Crew | 12-15 | [6 empty] | Roof Crew Meet, sign in
Begin Roof Construction - 2nd crew | 4 on lifting, 4 on setting, 2 on bracing, 1 on walking center, 2 on cut and carry | [7 empty] | Lift and set first end truss, plumb and brace
| 4 on lifting, 4 on setting, 2 on bracing, 1 on walking center, 2 on cut and carry | [7 empty] | Lift and set all center trusses, set 2' brackets, brace
| 4 on lifting, 4 on setting, 2 on bracing, 1 on walking center, 2 on cut and carry | [7 empty] | Lift and set final end truss, plum and brace
Begin Sheeting | 4 for facia, 4 to set sheeting, 2 to nail, 4 to cut and carry | [8 empty] | Install sub facia and first row sheeting
| 2 to insert, 2 to install | [8 empty] | Install web bracing inside trusses
Raise Scaffolds | All Truss crew | [8 empty] | Move scaffolds up, add guard rails
Truss Crew Break | [9 empty] | Break
| All Truss crew | [9 empty] | Truss crew Done
| 4 to cut and carry, 6 to set, 2 to nail | [10 empty] | Begin sheeting rest of roof
| 4 to roll out, 4 to nail, rest to clean up | [11 empty] | Install felt & drip edge
First Build Day Complete | [13 empty] | DONE
1) Top plates will be installed during build on outside walls with cut-outs for perpendicular inside walls (3.5" wide)
2) Top plates will be marked with truss locations
3) inside walls will have a top plate extension to overlap to first instersecting inside wall (3.5") and exterior wall (5.5")
4) Inside walls will be plumbed and braced to opposide corners during pre-building

## Sheet5
2019-06-01
T-1 | Floor
|  | 2" insulation |  | t-2 | t-1
|  | Beam |  | t-2 | t-1
|  | i-joists/rim |  | t-2 | t-1
|  | sub floor |  | t-2 | t-1
T-1+week | Prep
|  | materials to site |  | T-1+week
|  | trusses to site |  | T-1+week
|  | fly rafters built |  | T-1+week
|  | gable guard rails installed |  | T-1+week
|  | Cut crawl access |  | T-1+week
T-am | walls
|  | exterior |  | T-am
|  | Interior |  | T-am
|  | top plates |  | T-am
T-mid | scaffolding down |  |  | T-mid
T-pm | trusses
|  | spacers |  | T- pm
|  | lateral supports |  | T- pm
|  | hurricane clips |  | T- pm
roof
|  | sub facia |  | T- pm
|  | 1st row sheeting |  | T- pm
|  | scaffolding up |  | T- pm
|  | rest of sheeting |  | T- pm
|  | felt |  | T- pm
|  | drip edge |  | T- pm
| side door - temp |  |  | t-week
|  | styro |  | t-week
|  | door & frame |  | t-week
t+1 | porch roof
|  | porch surround |  | T+1
|  | temp posts |  | T+1
|  | trusses and supports |  | T+1
|  | Sub facia |  | T+1
|  | Sheeting |  | T+1
|  | felt |  | T+1
|  | valleys |  | T+1
|  | drip edge |  | T+1
T+1+week | shingles
|  | scaffolds off |  | T+1+week
concrete & gravel
|  | porch |  | T+1+week
|  | walks |  | T+1+week
|  | shed gravel |  | T+1+week
Mechanicals
|  | rough electric |  | T+1+week | T+3
|  | tub installed |  | T+1+week | T+3
|  | rough plumbing |  | T+1+week | T+3
T+2 | styro & tape |  |  | T+2
T+2 | windows & doors |  |  | T+2
T+2 | Box corners |  |  | T+2
T+2 | soffit/porch ceiling |  |  | T+2
T+2 |  | f channel |  | T+2
T+2 |  | facia |  | T+2
siding
T+2+week |  | corners |  | T+2+week
T+2+week |  | starter |  | T+2+week
T+2+week |  | j channel |  | T+2+week
T+3 |  | siding |  | T+3 | T+4
wall prep
T+3+week |  | drywall corners |  | T+3+week
T+3+week |  | rail blocking |  | T+3+week
T+3+week |  | curtain blocking |  | T+3+week
T+3+week |  | bath vent run |  | T+3+week
T+3+week |  | dryer vent installed |  | T+3+week
T+3+week |  | radon vent |  | T+3+week
wall insulation
T+3+week |  | window/foor |  | T+3+week
T+3+week |  | insul web |  | T+3+week
T+3+week |  | wall insulation |  | T+3+week
Drywall
T+4 |  | Instal |  | T+4
T+4+week |  | Finish |  | T+4+week
T+5 | Prime and Paint |  |  | T+5
Finish Mechanicals
T+5+week |  | Vinyl in HVAC |  | T+5+week
T+5+week |  | Electric |  | T+5+week
T+5+week |  | HVAC |  | T+5+week
Landscape
T+5+week |  | Grass seed |  | T+5+week | T+10
T+5+week |  | flower beds |  | T+5+week | T+10
Flooring
T+6 |  | laminate |  | T+6
T+6+week |  | vinyl |  | T+6+week | T+7+week
T+6+week |  | Carpet (if desired) |  | T+6+week | T+7+week
Interior Trim
T+7 |  | doors & knobs |  | T+7 | T+8
T+7 |  | window jambs |  | T+7 | T+8
T+7 |  | casings |  | T+7 | T+8
T+7 |  | base molding |  | T+7 | T+8
Cabinets
T+8 |  | cabinets |  | T+5+week | T+8
T+8 |  | counters |  | T+5+week | T+8
T+8 |  | knobs & handles |  | T+5+week | T+8
| Finish Plumbing |  | 3 week window
T+8+week |  | water heater |  | T+8+week | T+9+week
Racks and Rails
T+8+week |  | Closet shelves |  | T+8+week | T+9+week
T+8+week |  | bath rails |  | T+8+week | T+9+week
Accesses
T+8+week |  | Attic |  | T+8+week | T+9+week
T+8+week |  | Crawl |  | T+8+week | T+9+week
Deck
T+8+week |  | base molding |  | T+8+week | T+9+week
T+8+week |  | flooring |  | T+8+week | T+9+week
T+9 |  | stairs |  | T+9 | T+10+week
T+9 |  | railings |  | T+9 | T+10+week
Incidentals
T+9+week |  | Porch and door metal |  | T+9+week | T+10+week
T+9+week |  | Blinds |  | T+9+week | T+10+week
T+9+week |  | Appliances |  | T+9+week | T+10+week
T+9+week |  | Door locks |  | T+9+week | T+10+week
T+9+week |  | mail box & numbers |  | T+9+week | T+10+week
T+9+week |  | shutters |  | T+9+week | T+10+week
T+10 | OFF
T+11+1 |  | DEDICATION